## Sheet1
Task | Description | Assignee(s) | Priority | Status/Notes | Shown/Demo?
Sprint 3 Review Meeting | Date: April 12, 2024 | Kacie | 10 | Done at the end of Sprint 3 | ~
Sprint 3 Retrospective Meeting | Date: April 12th 2024 | Kacie | 10 | Done at the end of Sprint 3 | ~
Sprint 4 Planning Meeting | Date: April 12 2024 | Elya, Kacie | 2 | Done at the end of Sprint 3 | ~
Implement email verification | As a user, I want to verify my email so that I can create an account and receive notifications | Muiz | 1 | Will have to make popup green to match the rest of the site, and have the text fields auto tab | Y
Sprint 2 Review Meeting | Date: March 15, 2024 | Kacie | 1 | Done at the beginning of Sprint 3 | ~
Implement Dailies Page | As a user I want to log my habit’s completion and duration so that I can track my progress. | Max, Yifan | 1 | Habit part is working well, but to-do check in needs some work. We need a date picker in the top right. Streak counter has some bugs which need to be fixed in the back-end. Have to remove Frequency from Habit popups (not being implemented anymore) and change font style. Need dropdown for minutes/seconds/hours when selecting duration of a habit. Need to update streak counter in edit habit popup | Y
Sprint 2 Retrospective Meeting | Date: March 19th | Kacie | 1 | Done at the beginning of Sprint 3 | ~
Sprint 3 Planning Meeting | Date: March 19th | Elya, Kacie | 1 | Done at the beginning of Sprint 3 | ~
Username length restriction | Max characters: 20 | Muiz, Lysa | 3 | Done, tested | Y
Submit Progress Report 2 | Due: April 1, 2024 | Kacie | 5 | Submitted on April 1st, no feedback received | ~
Write Emails to be sent from site | Sending verification code, changing username, changing email, changing password, received friend request, someone accepted your friend request. | Kacie | 5 | Username change and password change email will just be changed to an "FYI" type email (password changing will be implemented in the front-end, not through emails). Changing email should send a verification code like on sign up. HTML is not useful/working (find a different way to auto generate?) | Y
API: POST Delete Friend, Send, Accept and Decline Friend Request (+ leaderboard) | schema function, route, controller function, testing full coverage | Lysa | 3 | Done | N
Implement Leaderboard Page | As a user, I want to be able to see the streaks of my friends, to encourage me to keep my own streak as high as possible. | Muiz | 7 | Fully functional, tested it with test account. Should bold the user's name, increase font size, add "My Leaderboard" title on the top | Y
Add so you can view your password if you want (login and sign up) | As a user, I want to have the option to be able to see my password as it is being typed in on the sign in and sign up pages. | Muiz | 10 | Done | Y
Update GitHub README with final info | Filled with final information, updated dates, and perhaps a link to the user manual. Images?? | Kacie | 10 | Done | Y
API: Habit CheckIn |  | Robbie | 1 | Done | N
API: Send Email | schema function, route, controller function, testing full coverage | Lysa | 1 | Done | N
API: Settings | schema function, route, controller function, testing full coverage | Lysa | 3 | Done | N
Update ER Diagram | For Progress Report 2 (Due April 1). | Lysa | 3 | Done, put into Progress Report 2 and submitted. | ~
Create accounts for professor for testing our app | mongodb admin account, email, HabitConnect account with friends and some habits. | Lysa | 3 | On the Discord server, to be emailed to the professor/TA on project submission | N
API: Notifications | schema function, route, controller function, testing full coverage | Lysa | 6 | Done | N
Create Installation Guide | Information on how to download the project from GitHub and run it from an IDE. | Kacie | 3 | Done, will give to friend to make sure instructions are clear, .env file code will need to be updated when email password is hidden from the GitHub history | Y
Implement User Profile Picture | As a user, I want to be able to have a picture to display on my profile for my friends to see. | Lysa | 5 | Got profile pictures uploading to the database, just isn't linked to the user's profile yet. Elya can add to the user profile as soon as this is done. | Y
Following tasks/user stories are still "in progress" and will be moved to Sprint 4
Stats APIs |  | Robbie, Lysa | 6 | In progress, but cannot be done completely until implementation of the My Stats page continues, since we need to know how graphs will be implemented | N
API: ToDo Checkin |  | Robbie | 1 | Mostly done, only needs to be tested and test cases created | N
Implement Settings Page | As a user, I want to be able to control my privacy settings and select what information other people can see on my profile. As a user, I want to be able to change my notification settings, to control the frequency of emails sent to me by HabitConnect. | Max | 1 | Max is almost done working on this. We will need to get rid of the style customization and accessibility options since we likely won't have time to implement (grey out and say "coming in the next update"?). API already created | Y
Implement API requests: User Profile |  | Elya | 2 | Still working on this, changes are being made slowly because of changes to friends APIs and user profile info updates requiring email work. Updating password shouldn't have the "forgot password" button - will be removed | Y
Add Profile Picture Component(drag and drop picture into box) |  | Elya, Lysa | 3 | Waiting on the implementation in the back-end, which was completed as of today, so this can be worked on further now. Place on user profile page is already prepared. | Y
Create User Manual | As a user I want a manual available which can teach me about all the features of the site, available to read in my own time. Required for final presentation/submission. | Kacie | 3 | User manual is in progress, just needs descriptions of each page and sccreenshots which are waiting on the finalized implementations of each page. | Y
Friend Request Function | As a user I want to be able to befriend people on the app so that I can share my progress and see theirs. | Elya, Lysa | 4 | Emails are now automatically being sent in the back-end thanks to Lysa, Elya just needs to make sure that all functionalities surrounding this are working. | N
Implement Notification Page | As a user I want to have all notifications visible at one place so that I can easily review and reply as needed. | Yifan | 4 | Yifan has not had time to work on this but APIs have been created, task assignment has changed to Elya. | Y
Updated Requirements Document | Required for final presentation/submission. | Kacie | 4 | This is currently in progress, but will be waiting on the finialized implementations of all pages to ensure that our requirements are being fulfilled. | Y
Add so when user changes their email, it confirms their new email by sending an email |  | Muiz | 5 | Template email has been created for this, partially implemented by Elya on the user profile page but will need assistance. | N
Implement My Stats Page | As a user I want to have different displays of my habit record with highlighted trends so that I can see patterns and improve my habits. | Max | 6 | Max is working on the .css of this page right now, very basic, need to be working on that soon. Stats API is being worked on by Robbie | N
Testing/Create Test Cases | Will be separated into more detailed backlog items during our testing phase in Sprint 3. Will involve writing test cases. | Kacie | 6 | Finalized testing will only be officially complete at submission of the final site, so this task will remain open until further notice. | ~
Implement Challenges Page | As a user, I want to be able to create group habits (challenges) for my friends to join so we can encourage each other to keep good habits. | Muiz, Max | 7 | Lysa will jump on back-end implementation for the group habits. We can reuse the habit creation/editing popups, and habit check-ins. Muiz has been working on it, just has not has time to finish it. | Y
Add random quotes for motivation in the back end |  | Elya, Lysa | 10 | Elya found a free API online to do this, will be moved to Sprint 4 with low priority (since we already have a temporary solution). | Y
Following tasks/user stories are still "to do" (not started) and will be moved to Sprint 4
Responsive Design | As a user I want to be able to use the web application on mobile or desktop screen so that I can access the website comfortably from any device. | Elya, Max | 1 | Still a working process on all pages, individually. | ~
Implement "Forgot Password" Functionality | As a user, I want to be able to reset my password from the sign in page if I forget it. | Muiz | 1 | Will be making a new email template for this, will definitely have to implement this sooner rather than later. Emaiin capabilities have already been completed. | ~
Better Password encryption | Encrypting before sending to back-end/db | Unassigned | 2 | Robbie did research into the topic of encrypting passwords, and we decided that we do not have to change our current implementation of encrypting passwords (encrypting on the server size, not storing plain texts) is sufficiently safe. Task will be deleted. | ~
Enable Mobile View |  | Elya | 6 | Elya will try to make it look viewable on mobile. | ~
Group Habit Pop-ups | For the Challenges page. | Max | 7 | With new implementation idea for the group habits on the challenges page, code will be reused and this task is no longer required. Task will be deleted. | ~
Test/Implement Keyboard Navigability | As a user, I want to be able to navigate the website using only keyboard functionality. | Kacie | 7 | Testing being moved to Sprint 4, since most of this manual testing should be done after implementation. | ~
Ensure Accessible Colour and Contrast | Use online colour checkers to ensure the site is meeting accessibility requirements. | Kacie | 7 | Testing being moved to Sprint 4, since most of this manual testing should be done after implementation. | ~
Cross-browser Compatibility Testing |  | Kacie | 7 | Testing being moved to Sprint 4, since most of this manual testing should be done after implementation. | ~
Test/Implement Screen Reading Compatibility | As a user, I want to be able to use a screen reader on the website. Accessibility requirement. | Kacie | 8 | Testing being moved to Sprint 4, since most of this manual testing should be done after implementation. | ~
Performance Testing |  | Kacie | 8 | Testing being moved to Sprint 4, since most of this manual testing should be done after implementation. | ~
Research hosting options | Part of the 5% bonus mark requirement. | Elya, Lysa | 9 | If we can do it, if not then it's fine. After the final presentation but before final report submission? | ~