## Sheet1
Task | Description | Assignee(s) | Difficulty | Status/Notes | Shown/Demo During Meeting?
Design Home Page | As a user I want to navigate to the home page so that I can learn more about the app and see the most important information. | Elya | 2 | done | Y
Design Dailies Page | As a user I want to log my habit’s completion and duration so that I can track my progress. | Kacie | 2 | done | Y
Implement basic reusable components | As a user I want to see a consistent design so that I can easily navigate the website. | Yifan | 5 | reqtool.js, apiRequest, done | Y
Design basic reusable components | As a user I want to see a consistent design so that I can easily navigate the website. | Kacie | 2 | done, in Figma | N
Set up project repository | Create a descriptive README file and set up the folder/file structure of some basic site functionality and documentation placeholders. | Kacie | 6 | done | N
Create style sheets | Have style sheets which will determine fonts, spacing, colours, etc. for the site, so that everything stays consistent and looks uniform across our pages of the site. Stylesheeets can be separated by component for better organization and reuse. | Yifan | 3 | basic ones are done, planning on moving all current .css files to a central css folder to maintain consistency | Y
Design Goal Creation Page | As a user I want to have a way to easily define my goals by providing the goal’s name, frequency, time in schedule, etc. so that I can start my new habit and track my progress effortlessly. | Kacie | 2 | "dailies" page, done | N
Implement Home Page | As a user I want to navigate to the home page so that I can learn more about the app and see most important information | Elya | 6 | have homepage implemented for those who are logged in, will still need something designed/implemented for guest users, and implement a few small details on this page when stats page is created | Y
Design Login page | As a user I want to be able to have a secure and straightforward log-in option so that I can access my account effortlessly. | Kacie, Elya | 2 | done | N
Implement Login page | As a user I want to be able to have a secure and straightforward log-in option so that I can access my account effortlessly. | Muiz, Yifan | 5 | needs formatting fixes, remove remember me checkbox, move forgot passsword | Y
Initialize Database | Initialize database with tables that will be needed and demo data. | Lysa, Robert | 3 | done | Y
Design Sign-up Page | As a user I want a secure and straightforward way to create an account so that my personal habit tracker data will be stored and I can review analytics. | Kacie | 2 | done | N
Set up Routers | Set up the router settings. Need to be done by both front-end and back-end. For example, the url of homepage might be “habitTracker/{user_id}/home”. | Yifan | 3 | done | Y
Create API Document | Back-end needs to design and write API document including API url, request format and response format and supported request type (GET/POST/DELETE). Back-end team should keep updating the document during the SE process. | Yifan | 3 | done, will be put in GitHub | Y
Create reusable API request functions in Front-end | We want some reusable code for HTTP/API requests. | Yifan | 2 | done | N
Create mock data to test log-in, log-out function in Front-end |  | Yifan | 2 | done, not needed anymore with database connected | Y
Secure User Registration and Authentication | Ensure proper and secure user registration and authentication through encryption | Lysa, Yifan | 5 | done | N
Create API response functions in Back-end | POST method for user sign-up POST method for user login (needs to be changed) GET method to get a user's goals (habits) | Robert, Lysa | 4 | done (to date) | Y
Design User Profile Page | As a user I want to have my personal information and settings displayed clearly so that I can review and edit my information, privacy and other settings easily. | Kacie, Elya | 2 | done | N
Submit Release Planning Document for Evaluation | Due: January 26, 2024 | Kacie | 4 | done | N
Sprint 1 Review meeting | Date: February 23, 2024 | Kacie | 2 | done | Y
Design Database models | Design the structure of database, draw a relational graph if possible. ER diagram and schema. | Robert, Lysa | 6 | done | Y
Create test data in the database |  | Robert, Lysa | 3 | done | Y
76 Total
Following tasks/user stories are still "in progress" and will be moved to Sprint 2
Implement Sign-up Page | As a user I want a secure and straightforward way to create an account so that my personal habit tracker data will be stored and I can review analytics. | Muiz | 5 | still needs many formatting fixes, and waiting on email verification to be implemented, about 80% done | Y
Implement Dailies Page | As a user I want to log my habit’s completion and duration so that I can track my progress. | Max | 8 | still needs a lot more work, scope was much larger than anticipated and was waiting on back-end work to be completed, not implemented into development branch in any capacity yet | N
Write unit tests for API request functions in Front-end | To be done after the back end is set up. | Yifan | 2 | started, not complete in time | N
Implement User Profile Page | As a user I want to have my personal information and settings displayed clearly so that I can review and edit my information, privacy and other settings easily. | Elya | 4 | started, not complete in time | N
Submit Progress Report 1 | Due: March 1, 2024 | Kacie | 5 | date changed to March 1, will be submitted following feedback from Brendan | Y
Create Privacy feature | Ensure a secure way to keep user’s data and make sure that users have full control. | Lysa | 3 | back-end work is in progress, but cannot be implemented properly until friends feature is implemented, which is not in this sprint | N
Set up automatic testing for back end API requests |  | Lysa, Robert | 6 | started, but we decided that testing would be focused on in later sprints | N
Guest User feature | As a guest user, I want to be able to explore some features of the app without creating an account so I can decide if I want to commit to creating an account. | Yifan | 4 | this task was determined to be a feature that needs to be considered for all pages, and thus this task is ongoing | Y
Report 1 Meeting with Brendan | February 27th at 3:00pm | Kacie | 3 | not until February 27th | ~
Following tasks/user stories are still "to do" (not started) and will be moved to Sprint 2
Implement Goal Creation: Popus on Dailies | As a user I want to have a way to easily define my goals by providing the goal’s name, frequency, time in schedule, etc. so that I can start my new habit and track my progress effortlessly. | Maxwell | 5 | cannot be done until base dailies page is implemented | ~