## Sheet1
Task | Description | Assignee(s) | Priority | Status/Notes | Shown/Demo?
Implement Challenges/Group Habits Page | As a user, I want to be able to create group habits (challenges) for my friends to join so we can encourage each other to keep good habits. | Muiz, Max | 1 | done, challenges can be created, joined, and are added to the dailies page as expected | Y
Implement Settings Page | As a user, I want to be able to control my privacy settings and select what information other people can see on my profile. As a user, I want to be able to change my notification settings, to control the frequency of emails sent to me by HabitConnect. | Max | 1 | done, working well with feedback for the user | Y
Fix the email templates | Per notes made in the Sprint3Tasks.xlsx document. | Kacie | 1 | done and new html scripting inserted into the document for ease of implementation | Y
API: Group Habits |  | Lysa | 1 | done | N
Fix Streaks | Streak values are not updating appropriately in the back end nor are they updating in the navigation bar. | Lysa, Elya | 1 | done, page does a quick reload to update the streak counter in the navigation bar, and streaks are mostly tracking appropriately, some bugs still found, but there is not enough time to rectify the issues | Y
Implement "Forgot Password" Functionality | As a user, I want to be able to reset my password from the sign in page if I forget it. | Muiz | 1 | done, working well and html implemented | Y
Responsive Design | As a user I want to be able to use the web application on mobile or desktop screen so that I can access the website comfortably from any device. | Elya, Kacie, Max | 1 | some pages are still not as responsive as we would like them to be, but most pages are usable on different screen widths/heights and we no longer have time to rectify issues on some of the other pages | Y
API - Privacy settings function with profile |  | Lysa | 2 | done | N
Finalize all emails sent in the backend | For notifying user if information for them in the database has been changed. | Lysa | 2 | done, html implemented | Y
Finalize Front End Emails (user sign up, forgot password, change email verification emails) | For sending the user verification codes, mostly just needed to implement the html. | Muiz, Kacie | 2 | done, html implemented | Y
Lots of Minor backend bug fixes |  | Lysa | 2 | done | N
Implement API requests: User Profile | Updating profile information | Elya | 2 | done | Y
Stats APIs |  | Robbie | 2 | done | N
Add Profile Picture Component(drag and drop picture into box) |  | Elya, Lysa | 3 | done, drag and drop is not implemented but you are able to upload images easily and they are displayed correctly (everything is updated in the back-end) | Y
Fix Notifications/Friends API | added "Friend" field in notifications, fixed so the "Message" field in notifications displays the following: if friend request sent: username+ " sent you a friend request!", if friend request accepted: usersName+ " accepted your friend request!", when sending a friend request it now returns "Friend Request Sent!" instead of the object information | Lysa | 3 | done, working well | Y
Implement Notification Page | As a user I want to have all notifications visible at one place so that I can easily review and reply as needed. | Elya | 4 | done, notifications can be cleared and friend requests can be accepted from the notification pop up | Y
Friend Request Function | As a user I want to be able to befriend people on the app so that I can share my progress and see theirs. | Elya, Lysa | 4 | done, along with notification pop up, displaying user information is working well | Y
Forgot password API | api for checking if the email exists, api for updating password based on the email | Lysa | 4 | done | N
Add so when user changes their email, it confirms their new email by sending an email |  | Elya | 5 | email works and sends verification code, everything is updated properly, html implemented | Y
Update friend view pop up based on privacy settings |  | Elya, Lysa | 5 | friend pop up works well, small css fixes were implemented, empty spaces when friends don't want to display specific information | Y
Updated Requirements Document | Required for final presentation/submission. | Kacie | 4 | document updated and added to the final report and README | Y
Implement My Stats Page | As a user I want to have different displays of my habit record with highlighted trends so that I can see patterns and improve my habits. | Max | 6 | only got one of the graphs working but the top of the page and quick insights are working well, and the one functioning graph seems to work well also, APIs are ready if we wanted to implement more graphs before final submission | Y
Dailies - add icon for habits that are group challenges |  | Kacie, Lysa | 6 | stars are added next to the names of habits in the dailies page that are a part of group challenges, and the user is informed that this is what this means | Y
Do remaining automated tests for the API I have made |  | Lysa | 6 | done | N
Testing/Create Test Cases | Will be separated into more detailed backlog items during our testing phase in Sprint 3. Will involve writing test cases. | Kacie | 6 | testing ideas document fully finished, testing master spreadsheet with the results of all manual tests uploaded to the GitHub | Y
Guest User Homepage | As a guest user, I want to be able to explore some features of the app without creating an account so I can decide if I want to commit to creating an account. | Max, Kacie | 7 | done and looks good, most responsive page on the site, screenshots are up to date | Y
Final Presentation | Final presentation with instructor and TA. Date: Apr 23 2024 @ 2:00-2:45pm | Kacie | 8 | done, notes uploaded to GitHub | ~
Add random quotes for motivation in the back end |  | Elya, Lysa | 10 | quote is randomly generated on page load | Y
update default profile pic to look nicer |  | Lysa | 10 | default user image with green background is now default for new accounts | Y
Sprint 4 Review Meeting | Date: April 26 2024 | Kacie | 9 | done | ~
Sprint 4 Retrospective Meeting | Date: April 26 2024 | Kacie | 9 | done | ~
Create User Manual | As a user I want a manual available which can teach me about all the features of the site, available to read in my own time. Required for final presentation/submission. | Kacie | 3 | done, linked and posted on GitHub | Y
Submit Final Report | Due: April 28, 2024 | Kacie | 10 | to be done shortly | Y
Video tutorial | WAITING on final site to film demonstration/get screenshots. | Lysa, Kacie | 10 | to be done shortly before submission of final report, will be created using recordings from the final presentation demonstration | Y
Following tasks/user stories were cancelled at the end of Sprint 4 and will not be completed
API: ToDo Checkin |  | Robbie | 1 | issues with todos in the front end were not able to be complete in a reasonable amount of time, therefore this task was canceled | N
Implement ToDo Check ins |  | Elya, Kacie, Muiz | 2 | no one who worked with the front-end could find enough time to fix the problems in this code, so we had to abandon getting the to do functionality connected to the back end properly | Y
Enable Mobile View |  | Elya | 6 | could not get done due to time constraints | ~
Test/Implement Keyboard Navigability | As a user, I want to be able to navigate the website using only keyboard functionality. | Kacie | 7 | could not get done due to time constraints, done in an informal capacity | ~
Ensure Accessible Colour and Contrast | Use online colour checkers to ensure the site is meeting accessibility requirements. | Kacie | 7 | could not get done due to time constraints, done in an informal capacity | ~
Cross-browser Compatibility Testing |  | Kacie | 7 | could not get done due to time constraints, done in an informal capacity | ~
Test/Implement Screen Reading Compatibility | As a user, I want to be able to use a screen reader on the website. Accessibility requirement. | Kacie | 8 | could not get done due to time constraints | ~
Performance Testing |  | Kacie | 8 | could not get done due to time constraints | ~
Research hosting options (optional) |  | Elya, Lysa | 11 | was always optional, decided not to pursue this at the end of the project, would have been too much to take on | ~