## Sheet1
Task | Description | Assignee(s) | Priority | Status/Notes | Shown/Demo?
Submit Progress Report 1 | Due: March 1, 2024 | Kacie | 1 | done, no feedback received | N
Write unit tests for API request functions in Front-end | To be done after the back end is set up. | Yifan | 2 | done | N
Report 1 Meeting with Brendan | February 27th at 3:00pm | Kacie | 3 | done, feedback included in progress report 1 and meeting notes | N
Implement Sign-up Page | As a user I want a secure and straightforward way to create an account so that my personal habit tracker data will be stored and I can review analytics. | Muiz | 3 | basic sign up functionality is fully working, only waiting on email verification (separate task) | Y
Implement User Profile Page | As a user I want to have my personal information and settings displayed clearly so that I can review and edit my information, privacy and other settings easily. | Elya | 4 | done, remaining work to be done split into other Jira tasks | Y
Add Streak Feature | As a user I want to keep track of how many days in a row I stayed consistent with my habit and get reminders so that I don’t miss my streak and stay motivated. | Yifan | 3 | done, some back end work needs to be done on dailies page to update streaks | Y
Implement Profile/Settings/Sign-out button | As a user I wan to have a button on user image icon so that I can access profile specific buttons: go to profile, open settings, and sign-out + remove journal + change to name in the corner | Yifan | 1 | done | Y
Design Notification Page/Popup | As a user I want to have all notifications visible at one place so that I can easily review and reply as needed. | Kacie, Elya | 3 | done | N
Design Analytics Page | As a user I want to have different displays of my habit record with highlighted trends so that I can see patterns and improve my habits. | Kacie | 5 | done | N
Design Challenges Page | As a user, I want to be able to create group habits (challenges) for my friends to join so we can encourage each other to keep good habits. | Elya | 6 | done | N
Design Guest Homepage | As a guest, I want to be able to see a preview of what the site looks like and what features are offered on HabitConnect without creating an account. | Kacie | 3 | done | N
Design Settings Page | As a user, I want to be able to control my privacy settings and select what information other people can see on my profile. As a user, I want to be able to change my notification settings, to control the frequency of emails sent to me by HabitConnect. | Elya | 2 | done | N
Design Profile Display Page (view profile as friend) | As a user, I want to see another users'/friends profile page so that I can learn more about them and get motivated from their achievements | Elya | 4 | done | N
Design Leaderboard Page | As a user, I want to be able to see the streaks of my friends, to encourage me to keep my own streak as high as possible. | Elya | 6 | done | N
API: GET Get User Habits |  | Robert, Lysa | 2 | done | N
API: POST Update Habit |  | Robert, Lysa | 1 | done | N
Set up automatic testing for back end API requests (+template) |  | Lysa, Robert | 3 | some of them are failing, but those are known errors that we will be fixing | Y
Full coverage for Testing Sign up, Login, and Delete User requests |  | Lysa | 4 | some bugs, but they are being worked on | Y
Create the routers and controllers for each schema |  | Lysa, Robert | 2 | will continue to be worked on as scale increases, but complete for now | N
Implement Goal Creation: Popus on Dailies | As a user I want to have a way to easily define my goals by providing the goal’s name, frequency, time in schedule, etc. so that I can start my new habit and track my progress effortlessly. | Max | 1 | done | Y
API: GET User Info | schema function, route, controller function, testing full coverage | Lysa | 2 | done | N
API: POST Delete friend |  | Robert, Lysa | 3 | done | N
Implement Update Habit function on Dailies page |  | Yifan, Lysa | 2 | done | Y
Implement Create new habit function on Dailies page |  | Yifan, Lysa | 2 | done | Y
Implement Get habits function on Dailies page |  | Yifan, Lysa | 2 | done | Y
Implement static Habit Manager popup on Dailies page |  | Max | 2 | done | Y
Implement static Edit Habit popup on Dailies page |  | Max | 2 | working, reminders element will be implemented when emailing is functional | Y
Implement static New Habit popup on Dailies page |  | Max | 2 | frequency not working yet, but otherwise this is completely working, will make a new task in Jira | Y
Implement static New Todo popup on Dailies page |  | Max | 2 | done | Y
Implement static Edit Todo popup on Dailies page |  | Max | 2 | done | Y
API: Edit User Information and Update User Password | schema function, route, controller function, testing full coverage | Lysa | 2 | done | N
API: POST Create Habit |  | Robert | 1 | done | N
API: POST Create ToDo |  | Robert | 1 | done | N
API: GET Todos |  | Robert | 1 | done | N
Sprint 2 Review Meeting | Date: March 15, 2024 | Kacie | 1 | done | Y
Make Notification Table | For notifications implementation. | Lysa, Robert | 3 | done | N
Make Statistics Table | For My Stats page implementation. | Robert, Lysa | 6 | done | N
Following tasks/user stories are still "in progress" and will be moved to Sprint 3
Implement Analytics Page | As a user I want to have different displays of my habit record with highlighted trends so that I can see patterns and improve my habits. | Kacie | 6 | started the layout of the page, still have to implement the graphs and link data to the database | N
Add Friends feature | As a user I want to be able to befriend people on the app so that I can share my progress and see theirs. | Elya | 2 | waiting on emailing functionality to be functioning in order to implement friend requests | Y
Implement API requests: User Profile |  | Elya | 2 | in progress, did not finish by meeting | Y
Guest User Homepage | As a guest user, I want to be able to explore some features of the app without creating an account so I can decide if I want to commit to creating an account. | Yifan | 2 | (waiting status), will be waiting on screenshots of completed pages to add to this page | Y
Implement Notification Page | As a user I want to have all notifications visible at one place so that I can easily review and reply as needed. | Yifan | 4 | started the notification pop up menu, not completed by meeting time | Y
Implement Dailies Page | As a user I want to log my habit’s completion and duration so that I can track my progress. | Max, Yifan | 1 | (waiting status) waiting on check-ins to be implemented in the back-end | Y
Implement Settings Page | As a user, I want to be able to control my privacy settings and select what information other people can see on my profile. As a user, I want to be able to change my notification settings, to control the frequency of emails sent to me by HabitConnect. | Max | 3 | being worked on, Max was having database connectivity issues so there was a delay in working on this | N
Implement email verification | As a user, I want to verify my email so that I can create an account and receive notifications | Muiz | 1 | continuing to run into problems, still working on it and needs support from someone in the back-end | N
Implement Leaderboard Page | As a user, I want to be able to see the streaks of my friends, to encourage me to keep my own streak as high as possible. | Muiz | 7 | almost done, did not finish by meeting | Y
Implement Challenges Page | As a user, I want to be able to create group habits (challenges) for my friends to join so we can encourage each other to keep good habits. | Muiz | 7 | pretty much done, just need to implement create new challenge pop-up | Y
Username length restriction | Max characters: 15 | Muiz, Lysa | 3 | basically done, only need to display a message to the user telling them they must keep their username under 15 characters | N
API: POST Delete Friend, Send, Accept and Decline Friend Request | schema function, route, controller function, testing full coverage | Lysa | 3 | in progress, send done but the others are still being worked on | N
Following tasks/user stories are still "to do" (not started) and will be moved to Sprint 3
Responsive Design | As a user I want to be able to use the web application on mobile or desktop screen so that I can access the website comfortably from any device. | Elya | 1 | is being constantly checked, this task being held as a reminder to check responsiveness of all web pages to different screen sizes | ~
Add Profile Picture Component |  | Elya, Lysa | 3 | not essential or started | ~
Create Privacy feature/settings | Ensure a secure way to keep user’s data and make sure that users have full control. | Lysa | 3 | waiting on settings page implementation | ~
Implement User Profile Picture | As a user, I want to be able to have a picture to display on my profile for my friends to see. | Lysa | 1 | not essential or started | ~
Add XP feature | As a user I want to earn XP from completing streaks and challenges so that I can be rewarded for my efforts, (increase my level in the app), and have a friendly competition with friends and other users. | Muiz | 6 | deleted, no longer implementing this | ~
Add reminder feature | As a user I want to receive reminders from the app about my goal so that I can keep on track with my habits and stay motivated. | Robert | 7 | deleted, will be separated into different stories | ~
Friend Request Function | As a user I want to be able to befriend people on the app so that I can share my progress and see theirs. | Elya | 4 | waiting on email functionality and back-end API requests | ~